## Milestone Burndown
Project Title: Milestone 1 Release #: 1.0 Sprint #: 1
| # | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 | As a dev I would like to have an initial design idea for the login page. | UI Design Mockup |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 2 | As a dev I would like to have an overview of the entire project and the tasks that it will take to bring the application to completion. | Create Sprint Product Log | Tim | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | As a dev I would like to have user stories and products outlined in the product log for the registration and login components. | Create user stories for Registration & Login page | Tim | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | As a dev I would like a high level breakdown of the current weeks tasks with time completion estimates and a chart for reference. | Create a sprint Burndown Chart | Tim | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | As a dev I would like to have the tasks listed in the burndown chart so the team can assign and complete the tasks for the application. | Update Burndown Chart | Tim | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | As a dev I would like to have a sprint backlog that contains the estimated task completion list for the current sprint. | Create Sprint Backlog | Tim | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | As a dev I would like to have the planning and estimation completed for the current sprint. | Update Sprint Backlog |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 6 | As a dev I would like to have documentation updated with our current progress and tooling. | Update design report | Tim/ Stephan | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | As a dev group we would like to hold a weekly meeting discussing strategies and progress. | Complete a retrospective | Tim/ Stephan | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | As a dev group we would like to analyze minesweeper code to determine what code is usable for this current project. | Analyze Minesweeper code | Tim/ Stephan | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | As a dev group we would like a centeralized location for code and project files for collaboration and version control. | Git server/ Create folder "Planning & Design" |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| 7 | As a group we should know who will do the final submit ahead of time to ensure a timely submission. Submission instructions are in the #resources page on Discord chat room. | Final Submission to Loud Cloud |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 13 | 11.14 | 9.29 | 7.43 | 5.57 | 3.71 | 1.86 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 13 | 7 | 7 | 7 | 7 | 7 | 7 | 7

## Sprint Backlog
Project Title: Milestone 1: Initial Scrum Planning Release #:1.0 Sprint #: 1.0
User Stories
ID | Feature | User Story | As a(n) <actor> | I would like to <description> | So that <outcome> | Priority | Sign-off Date | Modification Date
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Sprint Product Log
Project Title: Milestone 1: Initial Scrum Planning
User Stories
ID | Feature | User Story | As a(n) <actor> | I would like to <description> | So that <outcome> | Priority | Sign-off Date | Modification Date
1 | Login Page | As a user I would like to be able to login to the game site to access my saved games and other items related to my specific profile. |  |  |  | HIGH
2 | Registration Page | As a user I would like to create an account with the game site so that I can save games and view stats. |  |  |  | HIGH
3 | [5 empty] | MEDIUM
4 | [5 empty] | LOW
5